## Instructions
Onboarding plan office, instructions
Template by MetronHR: Office & knowledge work, for the first 90 days
1. Enter the employee and the start date at the top.
2. Deadlines are calculated relative to the start date (e.g. "-7" = one week before the start).
3. For each task: check the owner, set the status, add notes where needed.
4. For further employees: duplicate the "Plan" tab and fill it in again.
Tip: with MetronHR the onboarding plan becomes a reusable workflow; tasks are assigned automatically, owners get reminders and progress is recorded with owner and time.

## Plan
Onboarding plan office
Employee: |  |  | Start date: | 2026-05-31 22:00
Phase | Task | Owner | Deadline (days) | Due date | Status | Note
Before day 1 | Signed employment contract returned | HR | -14 |  | open
Before day 1 | Registration with social insurance & health insurer | HR | -7 |  | open
Before day 1 | Order hardware (laptop, monitor, headset) | IT | -10 |  | open
Before day 1 | Set up accounts (email, SSO, tools) | IT | -3 |  | open
Before day 1 | Prepare the workstation / keys & access card | Office | -2 |  | open
Before day 1 | Send a welcome email to the team | Team lead | -1 |  | open
Before day 1 | Welcome pack / desk prepared | Buddy | 0 |  | open
Week 1 | Personal welcome & office tour | Team lead | 0 |  | open
Week 1 | Hardware handover & setup | IT | 0 |  | open
Week 1 | Introduce the team & name a buddy | Team lead | 1 |  | open
Week 1 | Introduction to internal tools (Slack, Jira, etc.) | Buddy | 2 |  | open
Week 1 | Mandatory training: GDPR, data protection, compliance | HR | 3 |  | open
Week 1 | Reading: employee handbook, wiki, roles | HR | 4 |  | open
Week 1 | First 1:1 with the team lead | Team lead | 5 |  | open
Month 1 | Complete the onboarding training for each department | Team lead | 14 |  | open
Month 1 | Take on a first task independently | Buddy | 14 |  | open
Month 1 | Feedback meeting after 30 days | Team lead | 30 |  | open
Month 1 | Review access rights and adjust if needed | IT | 30 |  | open
Month 3 | Mid-probation review | Team lead | 60 |  | open
Month 3 | Agree goals for the end of probation | Team lead | 60 |  | open
Month 3 | Feedback round with the team & buddy | HR | 75 |  | open
Month 3 | End-of-probation review & decision on continued employment | Team lead | 89 |  | open
Template by MetronHR: www.metronhr.de ¦ Free to use within your business.