## Instructions
Onboarding plan practice, instructions
Template by MetronHR: Medical and dental practice, for the first 90 days
1. Enter the employee and the start date at the top.
2. Deadlines are calculated relative to the start date (e.g. "-7" = one week before the start).
3. For each task: check the owner, set the status, add notes where needed.
4. For further employees: duplicate the "Plan" tab and fill it in again.
Tip: with MetronHR the onboarding plan becomes a reusable workflow; tasks are assigned automatically, owners get reminders and progress is recorded with owner and time.

## Plan
Onboarding plan practice
Employee: |  |  | Start date: | 2026-05-31 22:00
Phase | Task | Owner | Deadline (days) | Due date | Status | Note
Before day 1 | Signed employment contract returned | Practice lead | -14 |  | open
Before day 1 | Registration with social insurance and health insurer | Practice manager | -7 |  | open
Before day 1 | Obtain proof of measles vaccination under section 20 (9) IfSG | Practice manager | -7 |  | open
Before day 1 | Prepare the confidentiality declaration under section 203 StGB | Practice lead | -5 |  | open
Before day 1 | Set up access to the practice management system and calendar | Practice manager | -2 |  | open
Before day 1 | Workwear, name badge, locker and keys | Practice manager | -2 |  | open
Week 1 | Welcome, practice tour, team introductions | Practice lead | 0 |  | open
Week 1 | Sign and file the confidentiality declaration | Practice lead | 0 |  | open
Week 1 | Practice management system training: appointments, patient records, billing | Practice manager | 0 |  | open
Week 1 | Hygiene plan, instrument reprocessing, protective equipment | Hygiene officer | 1 |  | open
Week 1 | Instruction under section 43 IfSG, where applicable | Hygiene officer | 1 |  | open
Week 1 | Radiation protection training, if X-rays are taken in-house | Practice lead | 2 |  | open
Week 1 | Emergency kit, emergency procedure, first aiders, escape routes | Safety officer | 2 |  | open
Week 1 | Phone and reception: greeting, judging urgency, recognising emergencies | Practice manager | 3 |  | open
Week 1 | Accompanied consultation hours, assisting at the treatment chair | Practice lead | 4 |  | open
Month 1 | Billing: fee codes, material records, quarterly close | Practice manager | 12 |  | open
Month 1 | Run reception independently, with back-up | Practice manager | 14 |  | open
Month 1 | Ordering, stock, expiry dates | Practice manager | 21 |  | open
Month 1 | Feedback meeting after 30 days | Practice lead | 30 |  | open
Month 3 | Identify training needs, plan mandatory briefings | Practice lead | 45 |  | open
Month 3 | Mid-probation review | Practice lead | 60 |  | open
Month 3 | Gather feedback from the team | Practice manager | 75 |  | open
Month 3 | End-of-probation review and decision on continued employment | Practice lead | 89 |  | open
Template by MetronHR: www.metronhr.de ¦ Free to use within your business.